## Risk_Register
Vendor Risk Register — CloudFlow Technologies
Nexus Financial Services ¦ Vendor: CloudFlow Technologies ¦ Product: CloudFlow CRM ¦ NEX-TPRM-2026-014 ¦ Report date: 2026-03-06
This is a fictional cybersecurity case study created for educational and portfolio purposes.
Risk ID | Risk Title | Description | Business Impact | Affected Asset | Control Domain | Likelihood | Impact | Inherent Risk | Existing Controls | Residual Likelihood | Residual Impact | Residual Risk | Risk Rating | Risk Owner | Treatment | Due Date | Status | Acceptance Required | Evidence Reference
VR-001 | Weak Subprocessor Governance | CloudFlow Technologies lacks a consistently documented and formally scored process for evaluating security risks associated with subprocessors. | A weakly governed subprocessor could expose Nexus Confidential CRM data to unauthorized access, availability disruption, or delayed incident awareness. | CloudFlow CRM customer and employee contact data; subprocessor chain | Third-Party / Subprocessor Management | 4 | 4 |  | Subprocessor inventory exists; contractual flow-down clauses for core AWS and selected SaaS utilities; annual review of named subprocessors without standardized risk scoring. | 3 | 4 |  |  | Jordan Hale, CISO, CloudFlow Technologies (Nexus TPRM owner: Priya Mehta) | Mitigate | 2026-04-30 | Open — remediation required before unrestricted production use | No — mitigate; residual High until remediation complete | Subprocessor_Management_Summary.pdf; Q-S-048; CTRL-TPRM-004
VR-002 | Insufficient Backup Recovery Testing | Backup restoration testing is performed annually only and may not provide sufficient evidence that critical CRM services can be recovered within expected timeframes. | Nexus sales operations, customer support, and relationship records could remain unavailable longer than business tolerance after a destructive incident. | CloudFlow CRM production data stores and backup media | Business Continuity / Backup Management | 4 | 4 |  | Daily encrypted backups; 30-day operational retention plus 12-month archive; annual restoration test of a non-production snapshot completed 2025-11-12. | 3 | 4 |  |  | Taylor Nguyen, Director of Infrastructure, CloudFlow Technologies | Mitigate | 2026-04-30 | Open — quarterly restoration testing required | No — mitigate; residual High until testing cadence improves | Backup_and_Recovery_Summary.pdf; Business_Continuity_Plan.pdf; Q-M-037
VR-003 | Undefined Recovery Point Objective | The vendor does not have a formally documented Recovery Point Objective (RPO) for the CloudFlow CRM platform. | Nexus cannot confirm maximum acceptable data loss. Daily backups imply up to approximately 24 hours of potential data loss, which may exceed Confidential CRM recovery expectations. | CloudFlow CRM platform availability and data integrity | Business Continuity / Disaster Recovery | 4 | 4 |  | Daily backups provide a de facto recovery point of approximately 24 hours; RTO of 8 hours is stated for the production CRM tier in the BCP, but RPO is not formally approved by business and technology owners. | 3 | 4 |  |  | Taylor Nguyen, Director of Infrastructure, CloudFlow Technologies | Mitigate | 2026-03-31 | Open — RPO must be documented and contractually committed | No — mitigate | Business_Continuity_Plan.pdf; Backup_and_Recovery_Summary.pdf; Q-L-033
VR-004 | Unclear Incident Notification SLA | The customer notification timeframe following a material cybersecurity incident is not clearly defined. Vendor language uses 'without undue delay' without a clock. | Nexus may be unable to meet its own regulatory, contractual, and customer notification obligations if CloudFlow delays notice after a material incident. | Nexus incident response and regulatory notification obligations | Incident Response | 4 | 4 |  | Formal incident response plan; severity classification; internal 24-hour executive escalation for Severity 1 events; customer notice described as 'without undue delay' and 'as required by law'. | 3 | 4 |  |  | Morgan Ellis, Director of Security, CloudFlow Technologies | Mitigate | 2026-03-31 | Open — contractual 24-hour material incident notice required | No — mitigate | Incident_Response_Plan.pdf; Q-J-028, Q-J-029
VR-005 | SOC 2 Type I Only | The available SOC 2 evidence is a Type I report dated 2025-09-30. Type I describes control design at a point in time and provides less assurance about operating effectiveness over a period than a Type II report. | Nexus has reduced independent assurance that described controls operated effectively throughout a review period. | Independent assurance over CloudFlow CRM control environment | Compliance | 3 | 3 |  | SOC 2 Type I (Security and Availability TSC) issued 2025-09-30; no qualified opinion on design; Type II examination in progress targeting 2026-Q4. | 2 | 3 |  |  | Jordan Hale, CISO, CloudFlow Technologies | Accept | 2026-12-31 | Accepted with conditions — Type II required as continuous monitoring evidence | Yes — CISO Nexus acceptance with Type II monitoring condition | SOC2_TypeI_Summary.pdf; Q-O-041
VR-006 | No ISO 27001 Certification | CloudFlow Technologies does not hold ISO/IEC 27001 certification. An internal ISMS exists and maps selected ISO 27001 control concepts, but no accredited certification has been obtained. | Absence of certification is not by itself a control failure, but it reduces external validation of the information security management system. | Information security management system assurance | Security Governance / Compliance | 3 | 3 |  | Documented information security policy; named CISO; annual policy review cycle; SOC 2 Type I; internal control mapping to ISO/IEC 27001 Annex A concepts. | 2 | 3 |  |  | Jordan Hale, CISO, CloudFlow Technologies | Accept | 2027-06-30 | Accepted with conditions — ISMS evidence accepted in lieu of certification | Yes — accepted provided annual independent assurance continues | Information_Security_Policy.pdf; Q-O-042; Q-A-003
VR-007 | Vulnerability Remediation Window | High-severity vulnerabilities may remain open for up to 30 days under the vendor vulnerability management policy. Critical findings target 7 days, but high-severity internet-facing issues can remain for a full month. | Known exploitable weaknesses in the CRM stack could persist long enough to be targeted, increasing the chance of confidentiality or availability impact. | CloudFlow CRM application and supporting AWS infrastructure | Vulnerability Management | 4 | 3 |  | Monthly authenticated vulnerability scanning; annual independent penetration test; WAF and security groups; 7-day target for Critical; 30-day target for High; exception process with CISO approval. | 3 | 3 |  |  | Morgan Ellis, Director of Security, CloudFlow Technologies | Accept | 2026-06-30 | Accepted with conditions — 15-day High SLA requested for internet-facing assets | Yes — accepted if internet-facing High findings meet 15-day target | Vulnerability_Management_Policy.pdf; Penetration_Test_Summary.pdf; Q-F-018
VR-008 | Legacy MFA Gap | Some legacy internal systems do not support multi-factor authentication. Privileged access to CloudFlow CRM production and AWS is MFA-enforced, but a small set of legacy administrative utilities still rely on password plus VPN. | Compromise of a legacy administrative credential could provide a pathway toward production support tooling if network segmentation fails. | Legacy internal admin utilities (not customer-facing CRM UI) | Identity and Access Management | 4 | 4 |  | MFA for production CRM, AWS IAM (privileged), and corporate SSO; VPN required for legacy tools; quarterly access reviews; privileged access via jump host for AWS. | 3 | 3 |  |  | Morgan Ellis, Director of Security, CloudFlow Technologies | Mitigate | 2026-05-15 | Open — MFA or compensating control required on remaining legacy admin tools | No — mitigate | Access_Control_Policy.pdf; Q-C-009

## Dashboard
Risk register dashboard
Nexus Financial Services ¦ Vendor: CloudFlow Technologies ¦ Product: CloudFlow CRM ¦ NEX-TPRM-2026-014 ¦ Report date: 2026-03-06
This is a fictional cybersecurity case study created for educational and portfolio purposes.
Metric | Value
Count of risks
High residual (rating High)
Moderate residual
Low residual
Critical residual
Treatments = Mitigate
Treatments = Accept
Overall vendor residual risk rating | High
Recommendation | Conditional Approval
This is a fictional cybersecurity case study created for educational and portfolio purposes.

## Scoring_Scale
5x5 scoring scale used by formulas
Nexus Financial Services ¦ Vendor: CloudFlow Technologies ¦ Product: CloudFlow CRM ¦ NEX-TPRM-2026-014 ¦ Report date: 2026-03-06
This is a fictional cybersecurity case study created for educational and portfolio purposes.
Score range | Rating
1–4 | Low
5–9 | Moderate
10–16 | High
17–25 | Critical
Formula | Risk Score = Likelihood × Impact