## Remediation_Plan
Corrective Action / Remediation Tracker
Nexus Financial Services ¦ Vendor: CloudFlow Technologies ¦ Product: CloudFlow CRM ¦ NEX-TPRM-2026-014 ¦ Report date: 2026-03-06
This is a fictional cybersecurity case study created for educational and portfolio purposes.
Finding ID | Finding | Required Action | Recommended Control | Responsible Owner | Priority | Due Date | Success Criteria | Evidence Required | Status | CAP ID
VR-001 | Weak Subprocessor Governance | Establish documented risk-based security assessments for all critical subprocessors, including a scored questionnaire, residual-risk rating, and approval record. | Formal subprocessor risk assessment procedure aligned to NIST SP 800-161 concepts | Jordan Hale, CISO, CloudFlow Technologies | High | 2026-04-30 | Approved subprocessor assessment procedure and completed assessments for all critical subprocessors, with scores retained for Nexus review. | Procedure document, completed assessments, residual-risk ratings, and contract flow-down evidence | Open | CAP-001
VR-002 | Insufficient Backup Recovery Testing | Perform documented restoration testing at least quarterly for critical CRM data stores and record recovery timing against RTO/RPO. | Quarterly backup restoration tests for production-equivalent datasets | Taylor Nguyen, Director of Infrastructure, CloudFlow Technologies | High | 2026-04-30 | Successful restoration test report with measured recovery timing for at least one production-equivalent restore. | Restoration test report, timestamps, issues log, and sign-off | Open | CAP-002
VR-003 | Undefined Recovery Point Objective | Define and formally approve a platform-specific RPO for CloudFlow CRM and reflect it in the BCP, customer contract, and backup design. | Documented and approved RPO (recommended: <= 4 hours for Confidential CRM data or compensating continuous backup) | Taylor Nguyen, Director of Infrastructure, CloudFlow Technologies | High | 2026-03-31 | Documented RPO approved by CloudFlow technology and business owners and committed in the Nexus MSA/DPA addendum. | Approved RPO statement, BCP update, and contractual exhibit | Open | CAP-003
VR-004 | Unclear Incident Notification SLA | Commit to a contractual customer notification SLA of 24 hours from confirmation of a material cybersecurity incident affecting Nexus data or services. | Contractual 24-hour material incident notification clause with named contacts | Morgan Ellis, Director of Security, CloudFlow Technologies; Samira Patel, Legal Counsel, Nexus | High | 2026-03-31 | Executed contract language specifying 24-hour notice, severity definitions, and communication channels. | Signed MSA/DPA security exhibit and updated IR plan notification matrix | Open | CAP-004
VR-005 | SOC 2 Type I Only | Provide a SOC 2 Type II report covering Security and Availability for a minimum six-month period, or an equivalent independent examination. | SOC 2 Type II (Security, Availability) as continuous monitoring evidence | Jordan Hale, CISO, CloudFlow Technologies | Moderate | 2026-12-31 | Unqualified Type II report covering the production CRM environment provided to Nexus TPRM. | SOC 2 Type II report (or documented delay with compensating evidence) | Monitoring — accepted with conditions | CAP-005
VR-006 | No ISO 27001 Certification | Maintain mapped ISMS evidence and provide annual independent assurance. ISO 27001 certification is encouraged but not a go-live blocker. | Continued SOC 2 / independent assurance and ISMS control mapping | Jordan Hale, CISO, CloudFlow Technologies | Low | 2027-06-30 | Annual independent assurance package received; optional ISO 27001 roadmap shared. | ISMS mapping workbook and next independent report | Monitoring — accepted with conditions | CAP-006
VR-007 | Vulnerability Remediation Window | Commit to a 15-day remediation target for High-severity findings on internet-facing CloudFlow CRM assets, with documented exceptions. | Differentiated SLA: Critical 7 days; internet-facing High 15 days; other High 30 days with exception register | Morgan Ellis, Director of Security, CloudFlow Technologies | Moderate | 2026-06-30 | Updated vulnerability policy and two months of ticket metrics demonstrating the 15-day internet-facing High target. | Updated policy and vulnerability SLA metrics | Monitoring — accepted with conditions | CAP-007
VR-008 | Legacy MFA Gap | Enforce MFA or a documented compensating control (hardware token or identity-aware proxy) on remaining legacy administrative utilities, or retire the systems. | MFA for all administrative access paths, including legacy tools | Morgan Ellis, Director of Security, CloudFlow Technologies | High | 2026-05-15 | Inventory of legacy admin tools showing MFA enabled or systems decommissioned, with access-review evidence. | Updated access control evidence and SSO/MFA coverage report | Open | CAP-008